## HLD
Task Name | Description | Status | Start Date | End Date | Duration | Comments
Website Designs | Get Website designs from the internet | Completed | 2023-03-11 |  |  | Gonna design as I go
CSS Libraries | Check which CSS library is easy to implement | Completed | 2023-03-11 | 2023-03-12 |  | Material UI
Redux | Check which Redux library to use. Learn the differences and advantages. | Not Started
CSS | Create a global CSS structure | Not Started

## Landing Page
Task Name | Description | Status | Start Date | End Date | Duration | Comments
First glance | Add a background image , food related. | Completed
Footer | Add footer at the bottom of the page | Not Started
Navbar | Add a Navbar on top. Navbar should have Logo, Add a Restaurant, Login, Signup. | In Progress | 2023-03-11 | 2023-03-18
Body | Add restaurants after the image. | In Progress
Navbar list | Write minimal code to show content in Navbar | Completed |  | 2023-04-01
Validation | Add input field validation in login and signup form | Completed | 2023-03-18 | 2023-03-19

## Partner with us
Task Name | Description | Status | Start Date | End Date | Duration | Comments
Sign Up form | Create a sign up form | Testing | 2023-04-02
Login form | Create a login form | Testing | 2023-04-02
Redirect | After signup, tell user to login. On login check if the token is valid and then redirect to registration page. If token is not valid, redirect to login page | In Progress | 2023-04-03

## Authentication
Task Name | Description | Status | Start Date | End Date | Duration | Comments | Design
Register | Add user Registration using email, password, role and name | Ready for QA |  | 2023-04-01
Login | Add login using email and password | Ready for QA |  | 2023-04-01